## Change List
Id | Breach status | Title | Phase Id | Service Display label | Owning group Name | Owner Name | Scheduled start | Scheduled end | Scheduled downtime start | Scheduled downtime end
16391345 | Breached and approved | P9A, P9E spare servers and Q9A 2nd app instance 25 decommissiong | Execute | SAP-S4-ERP_RAF_P9A | GBL_SAP-BASIS | Mundier, Vladimir | 2025-08-28 03:30 | 2025-09-21 03:30 | 2025-08-28 03:30 | 2025-09-21 03:30
12726131 | Breached and approved | SAP S/4 RSE Development system D8A upgrade | Execute | SAP-S4-ERP_RSE_D8A | GBL_SAP-BASIS | Bose, Sreejita | 2025-07-16 13:00 | 2025-08-11 | 2025-08-07 | 2025-08-09
11484750 | Breached and approved | Linde-SAP-MW2025: Global BI on HANA PRD systems (GPR, HPG, JPR) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP BW_GBL_GPR | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-12 03:30 | 2025-09-18 03:30 | 2025-09-14 09:30 | 2025-09-14 19:30
20550508 | Breached and approved | Linde-SAP-MW2025: PRD Global consolidated WD (WPA) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP_WEB-DISPATCHER_GBL_PRD | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-07 04:30 | 2025-11-13 04:30 | 2025-11-08 09:30 | 2025-11-08 19:30
11481330 | Breached and approved | Linde-SAP-MW2025: LE HANA DEV systems for ERP (VD1, HD1, JD1) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP ECC_LE-GBL_VD1 | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-10 03:30 | 2025-09-18 03:30 | 2025-09-11 09:30 | 2025-09-11 19:30
21016321 | Outside of maintenance window | 3600840 - [CVE-2025-42989] Missing Authorization check in SAP NetWeaver Application Server for ABAP | ApproveDeployment | SAP-S4-ERP_RAF_P9A | GBL_SAP-BASIS | Basak, Sudipta | 2025-09-26 | 2025-09-30
12137321 | Not calculated | JDR: Security Vulnerability Patch Upgrade | Plan | SAP BW_GBL_JDR | GBL_SAP-BASIS
20562185 | Outside of maintenance window | Linde-SAP-MW2025: EMEA Intouch Test ERP (GRA) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP R/3_INTOUCH_GBL_GRA | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-12 04:30 | 2025-11-20 04:30 | 2025-11-13 09:30 | 2025-11-13 19:30
7291032 | Breached and approved | GPA extreme slowness | Execute | SAP R/3_INTOUCH_GBL_GQA | GBL_SAP-BASIS | Patan, Imran Khan | 2025-06-04 20:00 | 2025-06-05 10:00
20555030 | Outside of maintenance window | Linde-SAP-MW2025: RUI S4 HANA Production systems (P1A, P1H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RUI_P1A | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-07 04:30 | 2025-11-13 04:30 | 2025-11-09 09:30 | 2025-11-09 19:30
10334842 | Breached and approved | S41 : NetApp storage migration from VSAN to NETAPP | Execute | SAP-S4-ERP_NA_D2A | GBL_SAP-BASIS | Gaal, Ivan | 2025-10-16 09:30 | 2025-10-16 21:30 | 2025-10-16 10:30 | 2025-10-16 20:30
8888618 | Breached and approved | S4A/S4H : NetApp storage migration from VSAN to NETAPP | Execute | SAP-S4-ERP_NA_D2A | GBL_SAP-BASIS | Gaal, Ivan | 2025-10-16 09:30 | 2025-10-16 21:30 | 2025-10-16 10:30 | 2025-10-16 20:30
20730275 | Not calculated | SR2 ¦¦ SAPROUTER ¦¦ Patch Update | Plan | SAP ROUTER-SR4-SR2_GBL_PRD | GBL_SAP-BASIS
11483170 | Breached and approved | Linde-SAP-MW2025: NativeDB for AdvAnalitics (HNP) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP BW_GBL_HNP | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-12 03:30 | 2025-09-18 03:30 | 2025-09-13 09:30 | 2025-09-13 19:30
7810870 | Outside of maintenance window | DGU/DGL Storage Migration from VSAN to NetApp | ApproveDeployment | SAP SCM_GBL_DGU | GBL_SAP-BASIS | bhattacharyya, Dwaipayan | 2025-07-22 10:00 | 2025-07-22 22:00 | 2025-07-22 10:00 | 2025-07-22 22:00
8751352 | Outside of maintenance window | LINDE ¦ DSM ¦ FRA ¦ MLGFRA10SA979 ¦ Decrease the RAM and CPU based on LDR8124_2612 :: PGG / PGN Hana Database | ApproveDeployment | GBL_TSI-MAINTENANCE_PRD | GBL_SAP-BASIS | Biswas, Sourav | 2025-07-11 12:30 | 2025-07-11 13:30 | 2025-07-11 12:30 | 2025-07-11 13:30
7812343 | Outside of maintenance window | PGU/PGL Storage Migration from VSAN to NetApp | ApproveDeployment | GBL_SAP-APO-PGU_PRD | GBL_SAP-BASIS | bhattacharyya, Dwaipayan | 2025-08-02 10:00 | 2025-08-03 | 2025-08-02 10:00 | 2025-08-03
10312507 | Breached and approved | Weekly MDM truncation for Quality System (pre-approved by normal change:- CR-16-018112) | Execute | SAP-SRM GBL_MQQ | GBL_SAP-BASIS | Biswas, Sourav | 2025-07-04 | 2027-12-31
10314573 | Breached and approved | Weekly MDM truncation for Quality System (pre-approved by normal change:- CR-16-018112) | Execute | SAP-SRM GBL_MQ1 | GBL_SAP-BASIS | Biswas, Sourav | 2025-07-04 | 2027-12-31
10315317 | Breached and approved | Weekly MDM truncation for Production System (pre-approved by normal change:- CR-16-018110) | Execute | SAP-SRM_GBL_MPP | GBL_SAP-BASIS | Biswas, Sourav | 2025-07-05 | 2027-12-31
10316183 | Breached and approved | Weekly MDM truncation for Production System (pre-approved by normal change:- CR-16-018110) | Execute | SAP-SRM_GBL_MP1 | GBL_SAP-BASIS | Biswas, Sourav | 2025-07-05 | 2027-12-31
11476113 | Breached and approved | Linde-SAP-MW2025: Global HR PRD systems (PGH) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP ECC_SAPHRON_GBL_PGH | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-05 03:30 | 2025-09-11 03:30 | 2025-09-07 09:30 | 2025-09-07 19:30
11476490 | Breached and approved | Linde-SAP-MW2025: Global HR SAP Gateway PRD (PGC) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP-NW-GATEWAY_PGC_GBL_PRD | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-05 03:30 | 2025-09-11 03:30 | 2025-09-07 15:30 | 2025-09-08 01:30
10170592 | Breached and approved | D1A storage migration from VSAN to NetApp | Execute | SAP-S4-ERP_RUI_D1A | GBL_SAP-BASIS | Gaal, Ivan | 2025-09-25 10:00 | 2025-10-03 | 2025-09-30 10:00 | 2025-09-30 20:00
11847156 | Outside of maintenance window | D9A/D9H : NetApp storage migration from VSAN to NETAPP | ApproveDeployment | SAP-S4-ERP_RAF_D9A | GBL_SAP-BASIS | Khatun, Sajinur | 2025-10-31 | 2025-11-07 | 2025-11-04 10:00 | 2025-11-04 20:00
11847990 | Outside of maintenance window | Q9A/Q9H : NetApp storage migration from VSAN to NETAPP | ApproveDeployment | SAP-S4-ERP_RAF_Q9A | GBL_SAP-BASIS | Khatun, Sajinur | 2025-10-31 | 2025-11-07 | 2025-11-06 10:00 | 2025-11-06 20:00
13091705 | Breached and approved | New Temporary system installation for S4 RSE upgrade - Y8A/Y8H | Execute | SAP-S4-ERP_RSE_Q8A | GBL_SAP-BASIS | Bose, Sreejita | 2025-07-21 | 2025-09-30
10173407 | Breached and approved | P1A storage migration from VSAN to NetApp | Execute | SAP-S4-ERP_RUI_P1A | GBL_SAP-BASIS | Rakshit, Rajarshi | 2025-10-08 | 2025-10-15 | 2025-10-12 08:30 | 2025-10-12 23:30
11660588 | Not calculated | P9E - Immediate Re-start Required | Plan | SAP ECC_BOCT_RAF_P9E | GBL_SAP-BASIS
11787010 | Breached and approved | Netapp restore on MLGFRA10SB586 from netapp storage | Execute | SAP R/3_INTOUCH_GBL_GRA | GBL_SAP-BASIS | Patan, Imran Khan | 2025-07-10 11:55 | 2025-07-10 16:00
10171968 | Breached and approved | Q1A storage migration from VSAN to NetApp | Execute | SAP-S4-ERP_RUI_Q1A | GBL_SAP-BASIS | Gaal, Ivan | 2025-10-01 | 2025-10-10 | 2025-10-06 10:00 | 2025-10-06 20:00
11454912 | Breached and approved | S9E : NetApp storage migration from VSAN to NETAPP | Execute | SAP ECC_BOCT_RAF_S9E | GBL_SAP-BASIS | Rej, Utsha | 2025-09-15 | 2025-09-30 | 2025-09-23 09:00 | 2025-09-23 23:00
11427404 | Breached and approved | VIM 7.6 SP8 Installation on T03 | Execute | SAP R/3_IMPRESS_REN_T03 | GBL_SAP-BASIS | Kaintura, Abhishek | 2025-07-14 | 2025-08-22
13670152 | Not calculated | RJ0 - Vulnerability component patching - Copy | Plan | SAP-NW-PO_GBL_RJ0 | GBL_SAP-BASIS
11478794 | Breached and approved | Linde-SAP-MW2025: DEV for Hana MDG-s and DPAgent (DTG, DTH, DTI) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP ECC_MDGS_GBL_DTG | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-05 03:30 | 2025-09-15 03:30 | 2025-09-08 09:30 | 2025-09-08 19:30
11783012 | Breached and approved | New Temporary system installation for S4 RSE upgrade - X8A/X8H | Execute | SAP-S4-ERP_RSE_D8A | GBL_SAP-BASIS | Bose, Sreejita | 2025-07-10 12:00 | 2025-08-30
15319713 | Not calculated | Open GQA for config | Plan | SAP R/3_INTOUCH_GBL_GQA | GBL_SAP-BASIS
15320288 | Not calculated | Netapp testing restore | Plan | SAP-ECC-BOCT_QGE_GBL_SBX | GBL_SAP-BASIS
20867030 | Breached and approved | SR2 ¦¦ SAPROUTER ¦¦ Patch Update | Execute | SAP ROUTER-SR4-SR2_GBL_PRD | GBL_SAP-BASIS | Mazumder, Samyukta | 2025-10-06 | 2025-10-10 | 2025-10-06 11:00 | 2025-10-06 13:00
14614742 | Breached and approved | De-commission S4 RAF TM0 ECC S91 (Oracle) System | Execute | SAP-S4-ERP_RAF_S91 | GBL_SAP-BASIS | Santosh Kumar, P V S R | 2025-08-04 | 2025-08-31
4874573 | Breached and approved | RAF PROD S4 HANA project: New systems build P9A | Execute | SAP-S4-ERP_RAF_Q9A | GBL_SAP-BASIS | Santosh Kumar, P V S R | 2025-05-19 | 2025-08-31
15324448 | Breached and approved | Netapp testing restore | Execute | SAP-ECC-BOCT_QGE_GBL_SBX | GBL_SAP-BASIS | Macejakova, Veronika | 2025-08-11 03:30 | 2025-11-06 04:30
15288609 | Breached and approved | Linde-SAP-MW2025: Global GTS QA ERP and HANA (QGG, QGN) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP GTS_GBL_QGG | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-13 03:30 | 2025-10-21 03:30 | 2025-10-14 09:30 | 2025-10-14 19:30
17921201 | Not calculated | Downsizing of tablespace PSAPTEMP and PSAPUNDO in GPA | Plan | SAP R/3_INTOUCH_4CE_GPA | GBL_SAP-BASIS
15285706 | Breached and approved | Linde-SAP-MW2025: Global SAP cloud connector Development (NCC) | Execute | SCP-CONNECTOR_GBL_DEV | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-10 03:30 | 2025-10-20 15:30 | 2025-10-13 13:30 | 2025-10-13 17:30
15284992 | Outside of maintenance window | Linde-SAP-MW2025: Global Portal PRD LISA & IMPRESS (P41) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP LISA-PORTAL_GBL_P41 | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-10 03:30 | 2025-10-16 03:30 | 2025-10-12 09:30 | 2025-10-12 19:30
15288401 | Breached and approved | Linde-SAP-MW2025: CoRE HANA PRD systems for BW (LPR, HPR) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP_CORE_GBL_LPR | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-16 03:30 | 2025-10-24 03:30 | 2025-10-17 09:30 | 2025-10-17 19:30
11477687 | Breached and approved | Linde-SAP-MW2025: Global DEV Systems for SRM/MDM (MD1, DSJ, DSG) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP SRM_GBL_DSG | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-05 03:30 | 2025-09-15 03:30 | 2025-09-08 09:30 | 2025-09-08 19:30
11270530 | Breached and approved | P8E ¦¦ storage migration from VSAN to NETAPP | Execute | RSE_BOCT-SAP-ERP-P8E_PRD | GBL_SAP-BASIS | Halder, Arpan | 2025-08-01 | 2025-08-24 | 2025-08-21 09:30 | 2025-08-21 22:30
10534595 | Outside of maintenance window | INFO Change ¦ LINDE ¦ FCI ¦ FRA ¦ Relocation servers CWD013 from cluster 2 to cluster 1 | ApproveDeployment | GBL_SAP-SERVICES | GBL_SAP-BASIS | Shetty, Pravin | 2025-07-02 11:30 | 2025-07-09 20:30
11479927 | Breached and approved | Linde-SAP-MW2025: Global Portal DEV LISA & IMPRESS (D41) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP PORTAL_GBL_D41 | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-08 03:30 | 2025-09-16 03:30 | 2025-09-09 09:30 | 2025-09-09 19:30
2460465 | Breached and approved | File System or Space addition for all DCO Production Servers for less than 400 GB (pre-approved via CR-17-017197) | Execute | SAP-BASIS-INTERNAL_GBL_PRD | GBL_SAP-BASIS | Bhattacharjee, Akash | 2025-04-23 23:00 | 2025-10-20
16738475 | Breached and approved | Memory increase in HQ1 ¦¦ MLGFRA10SA543 | Execute | SAP ECC_LE-GBL_VQ1 | GBL_SAP-BASIS | Mazumder, Samyukta | 2025-08-26 09:30 | 2025-09-02 23:30 | 2025-08-26 09:30 | 2025-08-26 11:30
20862956 | Outside of maintenance window | IBP Prod storage migration from VSAN to NetAPP | ApproveDeployment | SAP R/3_IMPRESS_REN_P01 | GBL_SAP-BASIS | bhattacharyya, Dwaipayan | 2025-10-26 08:00 | 2025-10-26 14:00 | 2025-10-26 10:00 | 2025-10-26 14:00
17384540 | Breached and approved | GPW/HPW storage migration from VSAN to NETAPP | Execute | SAP BW_GBL_GPW | GBL_SAP-BASIS | Mundier, Vladimir | 2025-10-04 08:30 | 2025-10-05 01:30 | 2025-10-04 09:30 | 2025-10-04 22:30
17951755 | Not calculated | Downsizing of tablespace PSAPTEMP and PSAPUNDO in GPA | Plan | SAP R/3_INTOUCH_4CE_GPA | GBL_SAP-BASIS
14171989 | Breached and approved | D0A Oracle system decommission. | Execute | SAP-S4-ERP_REN_D0A | GBL_SAP-BASIS | Boldizar, Tomas | 2025-07-28 19:00 | 2025-08-31 03:30
15285627 | Outside of maintenance window | Linde-SAP-MW2025: LE HANA PRD systems for ERP (VP1, HP1, JP1) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP ECC_LE-GBL_VP1 | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-10 03:30 | 2025-10-16 03:30 | 2025-10-12 09:30 | 2025-10-12 19:30
9353822 | Outside of maintenance window | PJ1/PJX : NetApp storage migration from VSAN to NETAPP | ApproveDeployment | SAP-NW-PO_GBL_PJ1 | GBL_SAP-BASIS | Khatun, Sajinur | 2025-10-08 | 2025-10-15 | 2025-10-11 10:00 | 2025-10-11 22:00
12179904 | Breached and approved | Linde-SAP-MW2025: LE HANA QAS systems for ERP (VQ1, HQ1) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP ECC_LE-GBL_VQ1 | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-24 03:30 | 2025-10-02 03:30 | 2025-09-25 09:30 | 2025-09-25 19:30
11958377 | Breached and approved | P6A/P6H storage migration from VSAN to NETAPP | Execute | SAP-S4-ERP_RGC_P6A | GBL_SAP-BASIS | Kumar, Abhishek | 2025-10-11 10:00 | 2025-10-20 23:00 | 2025-10-18 19:30 | 2025-10-19 05:30
9355210 | Breached and approved | RJ0/RJY : NetApp storage migration from VSAN to NETAPP | Execute | SAP-NW-PO_GBL_RJ0 | GBL_SAP-BASIS | Khatun, Sajinur | 2025-10-01 | 2025-10-08 | 2025-10-07 10:00 | 2025-10-07 20:00
9352365 | Breached and approved | RJ1/RJX : NetApp storage migration from VSAN to NETAPP | Execute | SAP-NW-PO_GBL_RJ1 | GBL_SAP-BASIS | Khatun, Sajinur | 2025-10-01 | 2025-10-08 | 2025-10-06 10:00 | 2025-10-06 20:00
11477272 | Breached and approved | Linde-SAP-MW2025: Global HR PRD systems (P50) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP-NW-JAVA_GBL_P50 | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-05 03:30 | 2025-09-11 03:30 | 2025-09-07 09:30 | 2025-09-07 19:30
20419842 | Not calculated | RJ0 - Vulnerability component patching - Copy | Plan | SAP-NW-PO_GBL_RJ0 | GBL_SAP-BASIS
9825517 | Breached and approved | D6A/D6H storage migration from VSAN to NETAPP | Execute | SAP-S4-ERP_RGC_D6A | GBL_SAP-BASIS | Kumar, Abhishek | 2025-10-06 | 2025-10-10 | 2025-10-07 10:00 | 2025-10-07 20:00
9830710 | Breached and approved | Q6A/Q6H storage migration from VSAN to NETAPP | Execute | SAP-S4-ERP_RGC_Q6A | GBL_SAP-BASIS | Kumar, Abhishek | 2025-10-03 10:00 | 2025-10-10 22:00 | 2025-10-09 10:00 | 2025-10-09 20:00
20362035 | Breached and approved | P9E : NetApp storage migration from VSAN to NETAPP | Execute | SAP ECC_BOCT_RAF_P9E | GBL_SAP-BASIS | Khatun, Sajinur | 2025-09-22 | 2025-09-29 | 2025-09-25 10:00 | 2025-09-25 20:00
17236792 | Breached and approved | Q8A Refresh from P8A | Execute | SAP-S4-ERP_RSE_Q8A | GBL_SAP-BASIS | Rana, Adarsh | 2025-08-22 10:00 | 2025-09-11 23:59 | 2025-08-27 | 2025-09-05 22:00
16387637 | Breached and approved | SAP S/4 RSE Quality system Q8A upgrade | Execute | SAP-S4-ERP_RSE_Q8A | GBL_SAP-BASIS | Bose, Sreejita | 2025-09-10 15:00 | 2025-10-02 15:00
18635173 | Breached and approved | Linde-SAP-MW2025: Global PrePRD Systems for PI/PO (RJ0, RJX) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP-NW-PO_GBL_RJ0 | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-28 04:30 | 2025-11-05 04:30 | 2025-10-29 09:30 | 2025-10-29 19:30
18637916 | Breached and approved | Linde-SAP-MW2025: RAF BOCT QA System ERP (S9E) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP ECC_BOCT_RAF_S9E | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-29 04:30 | 2025-11-06 04:30 | 2025-10-30 09:30 | 2025-10-30 19:30
20871764 | Outside of maintenance window | P9A/P9H : NetApp storage migration from VSAN to NETAPP | ApproveDeployment | SAP-S4-ERP_RAF_P9A | GBL_SAP-BASIS | Khatun, Sajinur | 2025-11-12 | 2025-11-19 | 2025-11-15 16:00 | 2025-11-16 06:00
12182594 | Breached and approved | Linde-SAP-MW2025: Global CFIN S/4 HANA DEV systems (DFG, DFH) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP CFIN_DFG_DEV | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-25 03:30 | 2025-10-03 03:30 | 2025-09-26 09:30 | 2025-09-26 19:30
19840588 | Breached and approved | LINDE ¦ DSM ¦ FRA ¦ Q2H/Q2A/S31 ¦ CPU and RAM increase based on LDR8187_2763 | Execute | GBL-SAP_TSI-LINUX | GBL_SAP-BASIS | Biswas, Rajiv | 2025-10-03 11:30 | 2025-10-03 15:30 | 2025-10-03 12:30 | 2025-10-03 14:30
18633988 | Breached and approved | Linde-SAP-MW2025: Dev Global consolidated WD (WNA) (WNA) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP_GBL_WEB DISPATCHER_QA | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-24 03:30 | 2025-11-03 04:30 | 2025-10-27 09:30 | 2025-10-27 19:30
18634600 | Breached and approved | Linde-SAP-MW2025: Intouch CUA development system (GDU) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP NW CUA_INTOUCH_GBL_GDU | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-27 04:30 | 2025-11-04 04:30 | 2025-10-28 09:30 | 2025-10-28 19:30
18635231 | Breached and approved | Linde-SAP-MW2025: Dev Global consolidated WD (WNB) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP_GBL_WEB DISPATCHER_QA | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-27 04:30 | 2025-11-04 04:30 | 2025-10-28 09:30 | 2025-10-28 19:30
20421187 | Outside of maintenance window | PJ1 - Vulnerability component patching | ApproveDeployment | SAP-NW-PO_GBL_PJ1 | GBL_SAP-BASIS | Sen, Avishek | 2025-10-06 | 2025-10-14 16:35 | 2025-10-12 10:00 | 2025-10-12 14:00
19856855 | Breached and approved | PB3 - Vulnerability component patching | Execute | SAP BW_LT_APAC_PB3 | GBL_SAP-BASIS | Rana, Adarsh | 2025-09-19 | 2025-09-26 16:35 | 2025-09-21 09:00 | 2025-09-21 14:00
18636133 | Breached and approved | Linde-SAP-MW2025: Global PrePRD Systems for PI/PO (RJ1, RJY) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP-NW-PO_GBL_RJ1 | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-29 04:30 | 2025-11-06 04:30 | 2025-10-30 09:30 | 2025-10-30 19:30
18637131 | Outside of maintenance window | Linde-SAP-MW2025: RUI S4 HANA Quality systems (Q1A, Q1H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RUI_Q1A | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-28 04:30 | 2025-11-04 04:30 | 2025-10-29 09:30 | 2025-10-29 19:30
16720163 | Outside of maintenance window | Linde-SAP-MW2025: Global SAP cloud connectors PRD (PCC,BCC) - Patching + OS image | ApproveDeployment | SCP-CONNECTOR_GBL_PRD | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-24 03:30 | 2025-10-31 04:30 | 2025-10-26 19:30 | 2025-10-27 01:30
16701962 | Outside of maintenance window | Linde-SAP-MW2025: RUI S4 HANA Development systems (D1A, D1H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RUI_D1A | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-21 03:30 | 2025-10-29 04:30 | 2025-10-22 09:30 | 2025-10-22 19:30
18638992 | Outside of maintenance window | Linde-SAP-MW2025: RAF S4 HANA Quality systems (Q9A, Q9H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RAF_Q9A | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-30 04:30 | 2025-11-06 04:30 | 2025-10-31 09:30 | 2025-10-31 19:30
7314494 | Breached and approved | Vsan storage decom for NetApp migrated systems | Execute | SAP SOLUTION MANAGER_LT_GBL_DMG | GBL_SAP-BASIS | Patan, Imran Khan | 2025-06-05 18:00 | 2025-12-29
18639800 | Outside of maintenance window | Linde-SAP-MW2025: EMEA Intouch QA ERP (GQA) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP R/3_INTOUCH_GBL_GQA | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-05 04:30 | 2025-11-13 04:30 | 2025-11-06 09:30 | 2025-11-06 19:30
16701928 | Outside of maintenance window | Linde-SAP-MW2025: RAF S4 HANA Development systems (D9A, D9H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RAF_D9A | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-22 03:30 | 2025-10-30 04:30 | 2025-10-23 09:30 | 2025-10-23 19:30
16703069 | Breached and approved | Linde-SAP-MW2025: Global PRD Systems for NWDI (P30) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP_NWDI_GBL_P30 | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-23 03:30 | 2025-10-31 04:30 | 2025-10-24 09:30 | 2025-10-24 19:30
16874985 | Breached and approved | RAF ECC BOCT Application servers decom P9E_27_AP,P9E_68_AP,P9E_67_AP,P9E_12_AP | Execute | SAP ECC_BOCT_RAF_P9E | GBL_SAP-BASIS | Biswas, Rajiv | 2025-08-28 | 2025-09-12
18951883 | Outside of maintenance window | Q8A/Q8H ¦¦ storage migration from VSAN to NETAPP | ApproveDeployment | SAP-S4-ERP_RSE_Q8A | GBL_SAP-BASIS | bhattacharyya, Dwaipayan | 2025-12-04 08:00 | 2025-12-04 22:00 | 2025-12-04 10:00 | 2025-12-04 20:00
18951621 | Breached and approved | D8A/D8H ¦¦ storage migration from VSAN to NETAPP | Execute | SAP-S4-ERP_RSE_D8A | GBL_SAP-BASIS | bhattacharyya, Dwaipayan | 2025-12-02 09:00 | 2025-12-02 21:00 | 2025-12-02 10:00 | 2025-12-02 20:00
16719473 | Outside of maintenance window | Linde-SAP-MW2025: Global CFIN S/4 HANA PRD systems (PFG, PFH) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP CFIN_PFG_PRD | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-24 03:30 | 2025-10-30 04:30 | 2025-10-26 09:30 | 2025-10-26 19:30
11479387 | Breached and approved | Linde-SAP-MW2025: LE HANA DEV systems for BW (VD4, HD4) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP BW_LE-GBL_VD4 | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-08 03:30 | 2025-09-16 03:30 | 2025-09-09 09:30 | 2025-09-09 19:30
18952156 | Outside of maintenance window | P8A/P8H ¦¦ storage migration from VSAN to NETAPP | ApproveDeployment | SAP-S4-ERP_RSE_P8A | GBL_SAP-BASIS | bhattacharyya, Dwaipayan | 2025-12-13 17:00 | 2025-12-14 11:00 | 2025-12-13 18:00 | 2025-12-14 08:00
19861853 | Breached and approved | P30: Security Vulnerability Patch Upgrade | Execute | SAP_NWDI_GBL_P30 | GBL_SAP-BASIS | Shah, Suraj | 2025-09-16 | 2025-09-22 | 2025-09-20 09:00 | 2025-09-20 14:00
11480979 | Breached and approved | Linde-SAP-MW2025: Welding/Retail QA ERP (QQE) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP ECC_4CE_RETAIL_QQE | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-09 03:30 | 2025-09-16 03:30 | 2025-09-10 09:30 | 2025-09-10 19:30
18622232 | Breached and approved | GSA - Decommission | Execute | SAP R/3_INTOUCH_GBL_GRA | GBL_SAP-BASIS | Santosh Kumar, P V S R | 2025-09-05 | 2025-09-30
10327034 | Breached and approved | SMD Installation for IBP servers | Execute | SAP R/3_IMPRESS_REN_D03 | GBL_SAP-BASIS | Kumar, Abhishek | 2025-07-29 15:25 | 2025-08-15
11471566 | Breached and approved | Linde-SAP-MW2025: Global BI on HANA QAS systems (GQR, HQG, JQR) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP BW_GBL_GQR | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-02 03:30 | 2025-09-10 03:30 | 2025-09-03 09:30 | 2025-09-03 19:30
11473432 | Breached and approved | Linde-SAP-MW2025: Global BI QAS system for SLT (QRG) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP_BW_GBL_QRG | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-03 03:30 | 2025-09-11 03:30 | 2025-09-04 09:30 | 2025-09-04 19:30
19841972 | Breached and approved | QSJ - Vulnerability component patching | Execute | SAP-SRM GBL_QSJ | GBL_SAP-BASIS | Mishra, Preity | 2025-09-17 11:00 | 2025-09-22 | 2025-09-18 10:00 | 2025-09-18 14:00
11482444 | Breached and approved | Linde-SAP-MW2025: Global BI Prod system for SLT (PRG, PRH) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP_BW_GBL_PRG | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-12 03:30 | 2025-09-18 03:30 | 2025-09-13 09:30 | 2025-09-13 19:30
16700620 | Outside of maintenance window | Linde-SAP-MW2025: EMEA Intouch DEV ERP (GDA) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP R/3_INTOUCH_GBL_GDA | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-22 03:30 | 2025-10-30 04:30 | 2025-10-23 09:30 | 2025-10-23 19:30
15427683 | Breached and approved | De-commission SAPHRON EHP8 temporary system MGH decom | Execute | SAP ECC_SAPHRON_GBL_MGH | GBL_SAP-BASIS | Biswas, Rajiv | 2025-08-12 | 2025-08-30
20564970 | Outside of maintenance window | Linde-SAP-MW2025: POSTFIX PRD1 - Operating System upgrade | ApproveDeployment | POSTFIX-SAP-EMAIL_GBL_PRD | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-20 04:30 | 2025-11-27 04:30 | 2025-11-21 10:30 | 2025-11-21 13:30
21046892 | Outside of maintenance window | Linde-SAP-MW2025: PRD for Hana MDG-s and DPAgent (PTG, PTH, PTI) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP ECC_MDGS_GBL_PTG | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-14 04:30 | 2025-11-20 04:30 | 2025-11-16 09:30 | 2025-11-16 19:30
20566253 | Outside of maintenance window | Linde-SAP-MW2025: RSE S4 HANA Quality systems (Q8A, Q8H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RSE_Q8A | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-13 04:30 | 2025-11-21 04:30 | 2025-11-14 09:30 | 2025-11-14 19:30
20548176 | Outside of maintenance window | Linde-SAP-MW2025: RSE S4 HANA Development systems (D8A, D8H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RSE_D8A | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-06 04:30 | 2025-11-14 04:30 | 2025-11-07 09:30 | 2025-11-07 19:30
15291440 | Outside of maintenance window | Linde-SAP-MW2025: Qas RSK Systems for S/4HANA (Q4A, Q4H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RSK_Q4A | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-13 04:30 | 2025-11-21 04:30 | 2025-11-14 09:30 | 2025-11-14 19:30
20563922 | Outside of maintenance window | Linde-SAP-MW2025: POSTFIX PRD - Operating System upgrade | ApproveDeployment | POSTFIX-SAP-EMAIL_GBL_PRD | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-13 04:30 | 2025-11-21 04:30 | 2025-11-14 10:30 | 2025-11-14 13:30
15157118 | Outside of maintenance window | Linde-SAP-MW2025: Dev RSK Systems for S/4HANA (D4A, D4H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RSK_D4A | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-06 04:30 | 2025-11-14 04:30 | 2025-11-07 09:30 | 2025-11-07 19:30
20862351 | Outside of maintenance window | IBP Non-prod storage migration from VSAN to NetAPP | ApproveDeployment | SAP R/3_IMPRESS_REN_D03 | GBL_SAP-BASIS | bhattacharyya, Dwaipayan | 2025-10-16 08:00 | 2025-10-16 16:00 | 2025-10-16 10:00 | 2025-10-16 14:00
15148646 | Breached and approved | Linde-SAP-MW2025: Global GTS Dev ERP and HANA (DGG, DGN) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP GTS_GBL_DGG | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-06 03:30 | 2025-10-14 03:30 | 2025-10-07 09:30 | 2025-10-07 19:30
15151220 | Breached and approved | Linde-SAP-MW2025: Global DEV Systems for PI/PO (DJ0,DJW) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP-NW-PO_GBL_DJ0 | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-07 03:30 | 2025-10-15 03:30 | 2025-10-08 09:30 | 2025-10-08 19:30
17383855 | Breached and approved | GDW/HDW storage migration from VSAN to NETAPP | Execute | SAP BW_GBL_GDW | GBL_SAP-BASIS | Mundier, Vladimir | 2025-09-23 08:30 | 2025-09-24 01:30 | 2025-09-23 09:30 | 2025-09-23 22:30
20556502 | Outside of maintenance window | Linde-SAP-MW2025: Prod RSK Systems for S/4HANA (P4A, P4H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RSK_P4A | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-21 04:30 | 2025-11-27 04:30 | 2025-11-23 09:30 | 2025-11-23 19:30
15155437 | Breached and approved | Linde-SAP-MW2025: Global CFIN S/4 HANA QAS systems (QFG, QFH) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP CFIN_QFG_QAS | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-09 03:30 | 2025-10-17 03:30 | 2025-10-10 09:30 | 2025-10-10 19:30
12227589 | Breached and approved | S4/Hana ¦ RNA ¦ TM2 ¦ System installation Q2A/Q2H Quality Hana box | Execute | SAP-S4-ERP_NA_D2A | GBL_SAP-BASIS | Gaal, Ivan | 2025-08-01 03:30 | 2025-09-30 03:30
21046051 | Breached and approved | Linde-SAP-MW2025: Intouch CUA PRD system (GPU) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP NW CUA_INTOUCH_GBL_GPU | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-14 04:30 | 2025-11-20 04:30 | 2025-11-15 09:30 | 2025-11-15 19:30
12179397 | Breached and approved | Linde-SAP-MW2025: QAS for Hana MDG-s and DPAgent (QTG, QTH, QTI) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP ECC_MDGS_GBL_QTG | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-19 03:30 | 2025-09-29 03:30 | 2025-09-22 09:30 | 2025-09-22 19:30
20551384 | Breached and approved | Linde-SAP-MW2025: PRD Global consolidated WD (WPB) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP_WEB-DISPATCHER_GBL_PRD | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-07 04:30 | 2025-11-13 04:30 | 2025-11-09 09:30 | 2025-11-09 19:30
9510158 | Outside of maintenance window | PJ0/PJY : NetApp storage migration from VSAN to NETAPP | ApproveDeployment | SAP-NW-PO_GBL_PJ0 | GBL_SAP-BASIS | Khatun, Sajinur | 2025-10-15 | 2025-10-22 | 2025-10-19 08:00 | 2025-10-19 22:00
16720268 | Outside of maintenance window | Linde-SAP-MW2025: Global GTS PRD ERP and HANA (PGG, PGN) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP GTS_GBL_PGG | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-24 03:30 | 2025-10-30 04:30 | 2025-10-26 09:30 | 2025-10-26 19:30
11471112 | Breached and approved | Linde-SAP-MW2025: LE HANA Sandbox systems for ERP (VX3, HX3) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Review | SAP ECC_LE_DE_VX3 | GBL_SAP-BASIS | Biswas, Sourav | 2025-08-29 03:30 | 2025-09-08 03:30 | 2025-09-01 09:30 | 2025-09-01 19:30
11454464 | Breached and approved | P7E : NetApp storage migration from VSAN to NETAPP | Execute | SAP ECC_BOCT_ASEAN_P7E | GBL_SAP-BASIS | Rej, Utsha | 2025-09-15 | 2025-09-30 12:00 | 2025-09-25 09:00 | 2025-09-25 23:00
21049340 | Outside of maintenance window | Linde-SAP-MW2025: RAF S4 HANA Production systems (P9A, P9H) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP-S4-ERP_RAF_P9A | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-14 04:30 | 2025-11-20 04:30 | 2025-11-16 09:30 | 2025-11-16 19:30
21047531 | Outside of maintenance window | Linde-SAP-MW2025: RAF PRD ERP (P9E) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP ECC_BOCT_RAF_P9E | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-14 04:30 | 2025-11-20 04:30 | 2025-11-16 09:30 | 2025-11-16 19:30
21045451 | Outside of maintenance window | Linde-SAP-MW2025: Global PRD Systems for SRM/MDM (MPP, MP1, PSJ, PSG) - OS Upgrade and Kernel Patching + implement EWA + Parameters | ApproveDeployment | SAP SRM_GBL_PSG | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-14 04:30 | 2025-11-20 04:30 | 2025-11-15 09:30 | 2025-11-15 19:30
20574655 | Outside of maintenance window | APO systems decommissioning- DGU/DGL, SGU/SGL, PGU/PGL | ApproveDeployment | GBL_SAP-APO-PGU_PRD | GBL_SAP-BASIS | Tripathi, Alok Kr | 2025-09-26 | 2025-10-06
19860084 | Breached and approved | P41 Security Vulnerability Patch Upgrade | Execute | SAP LISA-PORTAL_GBL_P41 | GBL_SAP-BASIS | Shah, Suraj | 2025-09-16 | 2025-09-24 05:00 | 2025-09-21 09:00 | 2025-09-21 14:00
20419578 | Outside of maintenance window | PJ0 - Vulnerability component patching | ApproveDeployment | SAP-NW-PO_GBL_PJ0 | GBL_SAP-BASIS | Sen, Avishek | 2025-10-06 | 2025-10-14 16:35 | 2025-10-12 14:00 | 2025-10-12 18:00
12179631 | Breached and approved | Linde-SAP-MW2025: Global Portal QAS LISA & IMPRESS (Q41) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP PORTAL_GBL_Q41 | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-22 03:30 | 2025-09-30 03:30 | 2025-09-23 09:30 | 2025-09-23 19:30
16906754 | Breached and approved | TGE - Decommission | Execute | SAP ERP_GBL_TGE | GBL_SAP-BASIS | Basak, Sudipta | 2025-08-30 | 2025-09-30
12176416 | Breached and approved | Linde-SAP-MW2025: Global QAS Systems for SRM/MDM (MQQ, MQ1, QSJ, QSG) (MQQ, MQ1, QSJ, QSG) - OS Upgrade and Kernel Patching + implement EWA | Execute | SAP SRM_GBL_QSG | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-19 03:30 | 2025-09-29 03:30 | 2025-09-22 09:30 | 2025-09-22 19:30
20577227 | Breached and approved | UC4 clean up after cutover RAF - P9E/Q9A/T9A | Execute | SAP-S4-ERP_RAF_Q9A | GBL_SAP-BASIS | Jezko, Pavol | 2025-09-22 03:30 | 2025-09-27 03:25
20033028 | Breached and approved | Memory downsizing of hana db server of P4A | Execute | SAP-S4-ERP_RSK_P4A | GBL_SAP-BASIS | Rej, Utsha | 2025-09-18 10:00 | 2025-09-24 15:00 | 2025-09-20 11:00 | 2025-09-20 14:00
19498040 | Outside of maintenance window | VIM 7.6 SP8 Installation on GQA | ApproveDeployment | SAP R/3_INTOUCH_GBL_GQA | GBL_SAP-BASIS | Shah, Suraj | 2025-09-23 11:00 | 2025-09-23 15:00
18029564 | Breached and approved | Downsizing of tablespace PSAPTEMP and PSAPUNDO in GPA | Execute | SAP R/3_INTOUCH_4CE_GPA | GBL_SAP-BASIS | Rej, Utsha | 2025-09-04 | 2025-09-19 | 2025-09-14 10:00 | 2025-09-14 14:00
12169811 | Breached and approved | Linde-SAP-MW2025: RASIA - China old PRD ERP (P6E) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP ECC_BOCT_RGC_P6E | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-18 03:30 | 2025-09-26 03:30 | 2025-09-19 09:30 | 2025-09-19 19:30
10663363 | Breached and approved | PEA ¦¦ storage migration from VSAN to NETAPP | Execute | SAP-ECC_LT_APAC_PEA | GBL_SAP-BASIS | Mazumder, Samyukta | 2025-09-13 12:30 | 2025-09-15 02:30 | 2025-09-13 14:30 | 2025-09-14 04:30
17223660 | Breached and approved | GRA system refresh from GPA | Execute | SAP R/3_INTOUCH_GBL_GRA | GBL_SAP-BASIS | Rej, Utsha | 2025-09-02 | 2025-09-17 | 2025-09-08 | 2025-09-15
20555713 | Outside of maintenance window | PFE ¦¦ Decommission of Azure system PFE | ApproveDeployment | SAP ECC_IN_PFE | GBL_SAP-BASIS | Mazumder, Samyukta | 2025-09-23 | 2025-10-07
19102976 | Breached and approved | Linde-SAP-MW2025: DEV SolMan Validate systems (DSN, DSH) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP SOLUTION MANAGER_LT_GBL_DSN | GBL_SAP-BASIS | Biswas, Sourav | 2025-11-05 04:30 | 2025-11-13 05:30 | 2025-11-06 09:30 | 2025-11-06 19:30
18638480 | Breached and approved | Linde-SAP-MW2025: POSTFIX-QA - Operating System upgrade | Execute | POSTFIX-SAP-EMAIL_GBL_DEV | GBL_SAP-BASIS | Biswas, Sourav | 2025-10-30 04:30 | 2025-11-07 04:30 | 2025-10-31 10:30 | 2025-10-31 13:30
20719140 | Not calculated | DGU/DGL Storage Migration from VSAN to NetApp - Copy | Plan | SAP SCM_GBL_DGU | GBL_SAP-BASIS
20971893 | Not calculated | Add 399 GB on server MLGFRA10SB502 | Plan | SAP CFIN_PFG_PRD | GBL_SAP-BASIS
12170645 | Breached and approved | Linde-SAP-MW2025: Welding/Retail PRD ERP (PQE) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP ECC_4CE_RETAIL_PQE | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-19 03:30 | 2025-09-25 03:30 | 2025-09-20 09:30 | 2025-09-20 19:30
19842482 | Breached and approved | PSJ - Vulnerability component patching | Execute | SAP-SRM_GBL_PSJ | GBL_SAP-BASIS | Mishra, Preity | 2025-09-19 11:00 | 2025-09-24 | 2025-09-20 11:00 | 2025-09-20 16:00
12172132 | Breached and approved | Linde-SAP-MW2025: LE HANA PRD systems for BW (VP4, HP4) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP BW_LE-GBL_VP4 | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-19 03:30 | 2025-09-25 03:30 | 2025-09-20 09:30 | 2025-09-20 19:30
12171570 | Breached and approved | Linde-SAP-MW2025: Non LT Production System for SRM LE (PSL) - OS Upgrade and Kernel Patching + implement EWA + Parameters | Execute | SAP SRM_LE-GBL_PSL | GBL_SAP-BASIS | Biswas, Sourav | 2025-09-19 03:30 | 2025-09-25 03:30 | 2025-09-20 09:30 | 2025-09-20 19:30
16349780 | Breached and approved | LINDE ¦ FCI ¦ UC4 Productive migration of Client 200 to version V24 | Execute | UC4-SCHEDULING-CLIENT200_GBL_PRD | GBL_SAP-BASIS-JOBMGMT | Kerschl, Peter | 2025-10-10 15:30 | 2025-10-13 15:30 | 2025-10-12 11:30 | 2025-10-12 15:30